## Local Plans
| WDA 1 | WDA 2 | WDA 3 | WDA 4 | WDA 5 | WDA 6 | WDA 7 | WDA 8 | WDA 9 | WDA 10 | WDA 11 | WDA 12 | ITSD
Counties | Clallam, Jefferson & Kitsap | Grays Harbor, Mason, Thurston, Pacific & Lewis | Whatcom, Skagit & San Juan Islands | Snohomish | King | Pierce | Wahkiakum, Cowlitz & Clark | Okanogan, Chelan, Douglas, Grant & Adams | Skamania, Kittitas, Yakima & Klickitat | Walla Walla, Columbia, Garfield, Asotin, Whitman, Ferry, Stevens, Pend Orielle, & Lincoln | Benton & Franklin | Spokane | ESD - ITSD The ITSD OCM Working Group Team (names in bold are part of the OCM planning team):
LWDB | Olympic Consortium WDC | Pacific Mountain WDC | Northwest Workforce Council | Future Workforce Alliance Board | Seattle King County WDC | Workforce Central | Workforce Southwest Washington | SkillSource North Central Workforce Development Board | South Central Workforce Development Council | Eastern Washington Partnership WDC | Benton-Franklin WDC | Spokane Workforce Council
Region | North Sound | Southwest Coastal | North Sound | North Sound | Central Sound | Central Sound | Southwest Coastal | Central | Central | East | East | East
Director / CEO | Bill Dowling | William Westmoreland | Gay Dubigk | James Henderson | Marie Kurose | Katie Condit | Miriam Halliday | Lisa Romine | Amy Martinez | Rod Van Alyne | Tiffany Alviso | Mark Matke / Dawn Karber
Regional Director | Jessica Barr | Tenille Johnson | Jessica Barr | Jessica Barr | Norton Sweet | Norton Sweet | Tenille Johnson | Todd Wurl | Todd Wurl | Jennie Weber | Jennie Weber | Jennie Weber
Sponsor(s) | Bill Dowling & Jessica Barr | Jason Hoseney & Tennille Johnson | Jessica Barr | James Henderson, Joy Emory & Jessica Barr | Marie Kurose & Norton Sweet | Katie Condit & Norton Sweet | Miriam Halliday & Tennille Johnson | Lisa Romine & Todd Wurl | Amy Martinez & Todd Wurl | Rod Van Alyne & Jennie Weber | Tiffany Alviso & Jennie Weber | Dawn Karber & Jennie Weber | Chrisa Castanon & Sumit Gupta
Change Manager | Liane Johnson | Cam McClary / Liane Johnson | Liane Johnson | Liane Johnson | Greg Chilson | Greg Chilson | Cam McClary / Liane Johnson | David Gutierrez Betancourt | David Gutierrez Betancourt | Liane Johnson | Liane Johnson | Liane Johnson | Kelly Ziesemer, Reddy Varakantham
Subject Matter Experts | Luci Bench Mike Robinson Jessica Brasher Jeff Allen Anjalee Blackwell | Kayla Flint Christina Chestnut Aaron Pentland Angie Rayfield Chris Skinner Cam McClary | Michelle Wilson, Kevin Logan, Shiloh Penland, Teresa Davis, Wendy Dobbs | Michelle Wilson, Jake Dryden, Alex Parle & Christina Tovar -Hamernik | Bryan Pannell (Performance) Michael Davie (Programs) Teri Holme (ROM) Deitra Garrett (Rainier) Kimberly Tickner (Auburn) | Shellie Willis (Sr. Director) Deborah Howell (COO) Joanna Rasmussen (Communications) Autumn Hughes (W-C) Sandra Calvillo (OSO) Teri Holme (ROM) Robbin Gard (Pierce) Elliott Sawyer (Pierce) | Amy Gimlin Chris Skinner Marnie Farness Teresa Anda Jessica Richards Marra Johnson Tana Haddenham | Susan Adams Aaron Parrott Emily Anderson Leonor Barker Craig Carrol Lora Wood | Meranda Smith (Director) Travis Piatz (COO) Jensie Rosenow (ISPC) Jesse Diaz (Sunnyside) Angie Mobley (Yakima) | Eric Blackburn, Brett Lancaster, Aja Woodruff, Michael Ensor, Stefanie Demmitt, Bryan Raines, Kelly Charlton, Lisa Mathias, Michelle Goodwin | David Chavey-Reynaud Jessie Cardwell Cynthia Garcia Crystal Bright Heather Woodruff Linda Rowling Rebecca Williamson | Liz Laubscher, Kate Martin, Greg Gormley, Tony Parks, Marlow Merritt, Brett Oliveri, Oscar Coronado, Becky Sommerville, Lori Veitenheimer, Steve Ruggles | Chad Stoker Rebecca McGinnis Ardriel Galvan Rob Allred Lawrence Banks Famous Atkison Krystin Boydstun Aaron Mason Vel Viswanathan Cuong Dang Dean Gruginski Dean Stainbrook Peter Sundholm Michele McMillin
Who will approve this plan? | Bill Dowling & Jessica Barr | Jason Hoseney & Tennille Johnson | Jessica Barr | James Henderson, Joy Emory & Jessica Barr | The entire OCM Team | The entrie OCM Team | Miriam & Tennille | The entire OCM Team | The entire OCM Team | Rod Van Alyne & Jennie Weber | Tiffany Alviso & Jennie Weber | Dawn Karber & Jennie Weber | The entire OCM Team
Who will be the approved sender of messages? | Luci Bench, and/or Jessica & Bill and Supervisors depending on message type | Emma Seymour, and/or Victoria Pruett will be main point of contacts and will disseminate as needed. | Jessica to administrators, administrators to supervisors, supervisors to staff | Jessica, Michelle or Liane to supervisors, ccing administrators then supervisors to staff – Unified messages from direct supervisors (Network for Change Group) | WDC = Michael Davie; ESD = Norton Sweet | WDC = Joanna Rasmussen; ESD = Norton Sweet | Julia Maglione, and/or Victoria Pruett will be main point of contacts and will disseminate as needed. Engaging Jessica and working with the Regional Change Agent | WDC - Aaron Parrott /Susan Adams: ESD = Todd Wurl | WDC = Meranda Smith; ESD = Todd Wurl | WDC Office Rod Van Alyne / Adminstrator &/or Jennie Weber | David Chavey-Reynaud | Liz Laubscher | Christa Castanon and/or Sumit Gupta
How often will team meet in 2023 | Monthly for 30 minutes – once closer to training 60 minutes a month. 2 months before training increase to biweekly | Starting in April once a month for an hour – once closer to training increase frequency of meetings.. 2 months before training increase to biweekly | Quarterly for 60 minutes – adhoc once we know training schedule | Monthly for 60 minutes | The team plans on meeting once a quarter. | The team plans on meeting once a quarter. | Starting in April once a month for 30 minutes – once closer to training increase to an hour. 2 months before training increase to biweekly | Will decide as roll out nears | Potentially once a quarter as project rollout nears | Adhoc for 30 minutes as needed | Quarterly for 60 minutes - once we know training dates increase to monthly | Quarterly for 60 minutes - once we know training dates increase to monthly | Quarterly or monthly
How will the team share information | WIT Monthly Meeting | All Staff Meetings | Teams Channel – summary sent out thru supervisors, team meetings & quarterly all staff meeting | Teams Channel – summary sent out thru supervisors, team meetings, Thursday all system meeting quarterly all staff meeting | All-staff meetings, e-mails, newsletters, 1:1’s, office visits, train-the-trainer | All-staff meetings, e-mails, newsletters, 1:1’s, FAQs | All Staff Meetings | All-staff meetings/huddles, newsletters, 1:1’s, office visits, train-the-trainer, peer-to-peer meetings, email updates | All-staff meetings/huddles, newsletters, 1:1’s, office visits, train-the-trainer, peer-to-peer meetings, email updates | emails with links | Share in meetings then email as follow up – review and get feedback Highly intentional as to include everybody | Share with leaders ans ask for input, Share in all staff meetings in January. Then email it out. | Division town halls, emails, IT division Pulse messages, newsletters, 1:1s, FAQs, WIT town halls
How will this team seek out feedback? Feedback loops | Monthly WIT meetings, Supervisors & Adhoc focus groups | Functional Teams, Supervisors/huddles, All-Staff meetings, Polls & Surveys | Team meetings, System meetings & Center Meetings Network for change All Leadership meetings Regional Townhalls | Network for change All Leadership meetings Regional Townhalls Team meetings System meetings Center meetings | All-staff meetings, office visits, 1:1’s | All-staff meetings, staff surveys, 1:1’s | All Staff Meetings Supervisors Program Teams | All-staff meetings, office visits, 1:1’s, pulse checks Strengths Unique to North Central | All-staff meetings, office visits, 1:1’s, pulse checks | Monthly meeting with WDA that include all of the partners Local office – Central contact person (POC for WDA10) Focus groups | OCM Team Supervisors SME’s (dedicated by functions/ influencers) Working committee We will use these adhoc | Supervisors, SME's, All Staff Meetings, Drop box - suggesions | Division town halls, emails, Teams polling features, Pulse messages, huddles, staff surveys, 1:1s
Why are we replacing ETO? | The current system doesn’t allow us to get to the level of details DOL requires. We need a system that supports our customers and stakeholders and allows us to spend more time with the customer and less time on data entry. | We are replacing ETO because we want to offer our customers a system that is more robust, easier to navigate, and that streamlines all of our processes, so they spend less time waiting and more time being heard and getting their needs met. Our new system will allow for faster and more accurate reporting which is good for us at the local level and for the PIRL that is submitted to DOL. We want the work we are doing to be captured and accurately reported. Interfacing with customers within the system will be game changing! The system will allow us the ability to assign customers tasks, and they will be able to upload docs directly with no need to repeat actions. It will be intuitive and help case managers create a workflow that makes sense to them. | We are replacing ETO because we want to offer our customers a system that is more robust, easier to navigate, and that streamlines all of our processes, so they spend less time waiting and more time being heard and getting their needs met. This will streamline the data entry for our staff lessoning the burden to do multiple entries to get the same information, streamline enrollments for our customers and will provide our leadership comprehensive reports that allow data to provide actual numbers and progression towards our goal and strategies for ESD. | WIT will improve the personnel and customer experience by, Increasing the number relevant reports Decreasing time to access reports Create an easily navigable UI Allow for data driven decision making processes Meet federal compliance & guidelines | Need a central source of data capture, shifting to a more user-friendly interface (WYSIWYG) with more current, intuitive and progressive technology, less time with keystrokes and more with time with customers (efficiency), where training will likely be easier (digital, JIT training). | The expectation is better reporting, better data capturing, potential for data sharing across partners, better serving the customer by allowing for more time to interact with the customer, and that the system is easier to use. | The WIT-ETO Replacement project is important because it will help to make work more efficient, data more accurate and will make our workforce system stronger. It will allow for faster and more accurate reporting which is good for us at the local levels and for the PIRL that is submitted to DOL. We want the work we are doing to be captured and accurately reported. Interfacing with customers within the system will be game changing, you can assign customers tasks, and they can upload docs directly and once. It will be intuitive and help case managers create a workflow that makes sense to them | Need a central source of data capture that is accurate and provides strong reporting, with potential for data sharing across partners. Shifting to a more user-friendly interface with more current, intuitive and progressive technology, requiring spending less time with keystrokes and more with time with customers (efficiency), where training will likely be easier. | Need a central source of data capture that is accurate and provides strong reporting, with potential for data sharing across partners. Shifting to a more user-friendly interface with more current, intuitive and progressive technology, requiring spending less time with keystrokes and more with time with customers (efficiency), where training will likely be easier. | The WIT – ETO Replacement project is important as it will provide ease of service access to our services for job seekers and a complete and efficient case management tool for staff providing services to them. It will also provide leadership, from the local level to the state’s executive level, the ability to review and report the good work being done throughout all our communities. | The WIT-ETO Replacement project is important because it will help to make work more efficient, data more accurate and will make our workforce system stronger. It will allow for faster and more accurate reporting which is good for us at the local levels and for the PIRL that is submitted to DOL. We want the work we are doing to be captured and accurately reported. Interfacing with customers within the system will be game changing, you can assign customers tasks, and they can upload docs directly and once. It will be intuitive and help case managers create a workflow that makes sense to them | We are replacing ETO because it does not meet the needs of customer-facing staff, nor does it satisfy federal reporting requirements or allow for accurate, real-time performance tracking. Our goal is to implement a streamlined, intuitive case management system that allows staff to focus on the customer rather than navigating the pitfalls of ETO, while also making it easier to access and analyze the data we spend so much time entering. The new system will meet all reporting requirements and will have the flexibility to adapt to future changes to keep us up-to-date and compliant. | The current system is slow, difficult to use, and doesn’t integrate with other systems or provide accurate data and reporting. To provide exceptional customer service we need a user-friendly technology system for employees and partners of the WorkSource partnership. To best serve the needs of the agency, the system must have data and reporting accuracy as well as the agility needed for future modifications and system integrations.
Strengths | • On a scale of 0-10, how are you feeling about the WIT-ETO replacement project (General pulse 7.3 tied for highest score) • I understand the goal of this change (Awareness) • I understand the risk of not changing (Awareness) • I understand the nature of the change’s impact on my work and workgroup (awareness) • I believe the training provided will give me what I need to be successful in this change. (Ability) • I can access additional knowledge and support when needed (Ability) • I can overcome any barrier to implementing this change in how I do my job (ability • Communication (69% positive) | Awareness • I understand the risk of not changing • I understand the nature of the change’s impact on my work and my group Knowledge • I have the capacity to learn the new things I need to be successful in this change. | • I understand the nature of the change’s impact on my work and workgroup (awareness) • I believe the change is worth it and outweighs not changing (desire) • I have the capacity to learn the new things I need to be successful in this change • I can overcome any barrier to implementing this change in how I do my job (ability | • On a scale of 0-10, how are you feeling about the WIT-ETO replacement project – 6.8 (avg 6.5) (general pulse) • I understand the goal of this change (awareness) • I understand the risk of not changing (awareness) • I understand the nature of the change’s impact on my work and my group (awareness) • I believe the organizational motivation for this change are true and accurate. (desire) | • King County has a history of using an integrated training approach. • Partnership between WDC and ESD, partners is strong; there is a willingness to work together • Adaptability; most likely to encounter the issues, thus solve the issues; • Communication; newsletter; intranet (learning exchange) • Size offers something special; variety of programs; ability to test the waters; exploratory; embracing, getting in front of change (culture) • Thought leaders, but willing to ‘steal shamelessly’ from others; make the wheel rounder | • Staff buy-in (agreement) • Proactive, effective way to roll this system out (change management) • Communication from team • Customer needs concerning data collection | Awareness • I understand the goal of this change (89%) • I understand the risk of not changing (82%) • I understand the nature of the change’s impact on my work and my group (75%) Desire • I believe making the change is worth it and outweighs not changing. (85%) • There is a compelling business need for WIT-ETO Replacement project. (89%) | • Knowledge of the current data in ETO, staff understand that data is needed and that we are performance driven. • Partnership between WDC and ESD, partners is strong; there is willingness to work together. • Adaptability: most likely to encounter the issues, thus solve the issues; • Variety of programs; ability to test the waters; exploratory; embracing, getting in front of change (culture). • Proactive, effective way to roll this system out (change management) | • Knowledge of the current data in ETO, staff understand that data is needed and that we are performance driven. • Partnership between WDC and ESD, partners is strong; there is willingness to work together. • Adaptability: most likely to encounter the issues, thus solve the issues; • Variety of programs; ability to test the waters; exploratory; embracing, getting in front of change (culture). • Proactive, effective way to roll this system out (change management | • I understand the goal of this change (awareness) • I understand the risk of not changing (awareness) • I understand the nature of the change’s impact on my work and my group (awareness) • I believe the training provided will give me what I need to be successful in this change (ability) • I can access additional knowledge and support when needed. (ability) • I can overcome any barrier to implementing this change in how I do my job. (ability) | • There is a compelling business need for the WIT ETO Replacement (100%) • I believe making the change is worth it and outweighs not changing. (desire) • I have the capacity to learn the new things I need be successful in this change. (knowledge) • I can overcome any barrier to implementing this change in how I do my job. (ability) | • There is a compelling business need for the WIT ETO Replacement (96%) • I understand the goal of this change (awareness) • I believe the organizational motivations for this change are true and accurate. (desire) • Staff want it, staff need it – they are looking forward to a better system • 72% of staff understand the risk of not changing • 80% can overcome any barriers on how to do my job | • Knowledge of current system, IT and data analytics • Vendor/technology collaboration (vendor, business, WaTech, Product Management liaison) • Resilient group (used to lots of change and able to keep working through change) • Understanding of statewide IT policies and legal considerations • Securing data • Architecture • Consulting in technology forecasting, trending, integration
Opportunites | • I know what is in it for me (Desire) • I have been able to voice my objections and they have been taken into consideration (Desire) • I have the knowledge I need to be successful after the change is implemented. (Knowledge) | • Low score on how are you feeling about the WIT-ETO replacement project at 5.6 Desire • I know what’s in it for me (WIIFM) • I believe the organizational motivations for this change are true and accurate • I have been able to voice my objections and they have been taken into consideration Knowledge • I clearly understand the impact this change will have on my behaviors, processes, tools, and workflow • I have been able to voice my objections and they have been taken into consideration • Resources and tools are available to help me be successful | • Communication (50% somewhat effective) • I have the knowledge I need to be successful after the change is implemented (knowledge) • Resources and tools are available to help me be successful • There are mechanisms in place to sustain the change (Reinforcement) | • Communication • I believe the training provided will give me what I need to be successful in this change (ability) • I can access additional knowledge and support when needed. (ability) • I can overcome any barrier to implementing this change in how I do my job. (ability) | • More opportunities for collaboration; support each other’s deliverables and outcomes • Meet customers where they are (literally, physically); connection sites; representation at connection sites • Identifying new opportunities • Work beyond WIOA programs; nimble enough to leverage with other programs; wrap-around services | • Lots of redundancies • Not collecting the voice of the customer, those impacted in real time • Not fixing issues in a timely manner, which has cascading effect • Accountability of the vendor • Clarity, or lack of | • Lowest score on how are you feeling about the WIT-ETO replacement project at 5.5 Desire • I know what’s in it for me (WIIFM) (36%) • I believe the organizational motivations for this change are true and accurate (64%) • I have been able to voice my objections and they have been taken into consideration (21%) Knowledge • I clearly understand the impact this change will have on my behaviors, processes, tools, and workflow (43%) • I have the knowledge I need to be successful after the change is implemented (36%) | • More opportunities for collaboration; support each other’s deliverables and outcomes. • Meet customers where they are (literally, physically); connection sites; representation at connection sites. • Identifying new opportunities. • Work beyond WIOA programs; nimble enough to leverage with other programs; wrap-around services. | • More opportunities for collaboration; support each other’s deliverables and outcomes. • Meet customers where they are (literally, physically); connection sites; representation at connection sites. • Identifying new opportunities. • Work beyond WIOA programs; nimble enough to leverage with other programs; wrap-around services. | • Skepticism • There are mechanisms in place to sustain the change. (reinforcement) • Our organization is committed to keeping the change in place. (reinforcement) • I have an outlet for providing feedback on the change. (reinforcement) | • Communication • Partner engagement • I have been able to voice my objections and they have been taken into consideration (desire) • I understand the nature of the change’s impact on my work and my group. (awareness) | • There are mechanisms in place to sustain the change. (reinforcement) • I have an outlet for providing feedback on the change. (reinforcement) • I have been able to voice my objections and they have been taken into the consideration. • 49% believe the training will be sufficient (people learn in different ways, need local training ops | • Accountability all around – Sups/Mgrs to hold staff accountable (duties/due dates, etc.), and Sups/Mgrs are accountable as well • Leverage talent and skills appropriately • Prioritization • Long-term planning (including future system capabilities and portfolio management to prevent working in firefighting mode) • Communication (about priorities and in general) • Engagement (avoid multitasking during town halls, huddles, etc.)
What will success look like? | • Staff would be spending 80% time on customers/20% other (meetings, data entry, etc.) • Clean data migration • Easy to pull reports • Clean PIRL • DOL – will say “beautiful” • Clean data we can trust • All staff trained up to date using system • Good roll out to customer • Check ins will help us gauge success along the way – giving us the ability to adjust as we go • Staff will define success – their ability to use system and it works – it is doing what we said it would do • Take feedback and follow up with results • We will have a big party celebration!!!! | • JOY – NO MORE ETO • More time with customer and less time on data entry • Clean data migration • Easy to pull reports • Clean PIRL • DOL – will say “beautiful” • Data we can trust • All staff trained up to date using system • Good roll out to customer (self-service options) • Check ins will help us gauge success along the way – giving us the ability to adjust as we go • Staff will define success – their ability to use system and it works – it is doing what we said it would do • Take feedback and follow up with results • We will have a big party celebration!!!! | • Success looks like staff being able to spend 80+% of their time (at least) on customers rather than current state which is more like 50% with the rest being on entering data into multiple systems. • Streamlined customer service with referrals, access, and opportunity to the multiple services. • A system that meets 85% to 90% of our needs • Staff is engaged and excited about the new tool • Positive attitudes and people have been able to participate with feedback and have had concerns addressed • Staff is adequately trained and are equipped to use the new system • Resources are available when staff need it • Staff is able to articulate the wins with the new system and the benefits • Everybody has access to data that is accurate and timely, and it is easy to pull in one place. | • Success looks like staff being able to spend 80+% of their time (at least) on customers rather than current state which is more like 50% with the rest being on entering data into multiple systems. • Streamlined customer service with referrals, access, and opportunity to the multiple services. • A system that meets 85% to 90% of our needs • Staff is engaged and excited about the new tool • Positive attitudes and people have been able to participate with feedback and have had concerns addressed • Staff is adequately trained and are equipped to use the new system • Resources are available when staff need it • Staff is able to articulate the wins with the new system and the benefits | • Access to the data, in a useable format • Create ad hoc queries from the database • Less burden in the documentation process • If there’s complaining, then successful • User-friendly platform that gets us the information we can use/we need • Will start winning people over once they get to touch and feel new product • Ability to make useful, accurate decisions on processes, on how the system operates, using the data on how we do business | • Early adoption of tools, functions to run system • Pain points identified early, and addressed • System delivers what is promised, and within timeframe allotted • Duplicative data removed, just what we need is included • Roll-out is done in a way that front-line staff embraces, is included • Functionality broad enough for all users, regardless of program • Customer experience is seamless, as if now system is present | • JOY – NO MORE ETO • More time with customer and less time on data entry • Clean data migration • Easy to pull reports • Clean PIRL • DOL – will say “beautiful” • Data we can trust • All staff trained up to date using system • Good roll out to customer (self-service options) • Check ins will help us gauge success along the way – giving us the ability to adjust as we go • Staff will define success – their ability to use system and it works – it is doing what we said it would do • Take feedback and follow up with results • We will have a big party celebration!!!! | • Efficiency and effectiveness to help save staff time and use that time with customers • Being able to get the data out that we put in, being able to get accurate report out, in a useable format • Front line staff feeling comfort with the system, feeling confident • Needs to add value and be more efficient to empower staff to do their job confidently • Less burden in the documentation process • User-friendly platform that gets us the information we can use/we need • Ability to make useful, accurate decisions on processes, on how the system operates, using the data on how we do business. • Functionality for all users, regardless of program, while having a strong support system after the roll out in order to deal with problems that come up. | • Access to the data, in a usable format • Less burden in the documentation process • User-friendly platform that gets us the information we can use/we need • Will start winning people over once they get to touch and feel the new product • Ability to make useful, accurate decisions on processes, on how the system operates, using the data on how we do business. • Functionality for all users, regardless of program • Make sure the users feel heard, their feedback embraced • Customer experience is seamless, almost as if no system is present • Less time looking at keystrokes, more at the customer’s face • System integration, removes repetition | • More efficient employees • Less duplication of work • Less frustration • Happy customers that are getting their basic needs met • Accurate reporting / metrics • People are using the metrics for data driven decision making • More time to focus on customer success • We will no longer be thinking about the reporting part of our job as a chore | • Staff would be spending 80% time on customers/20% other (meetings, data entry, etc.) • Reports are easy to run, and you can trust the data • Less duplication of data entry • Increase in positive customer engagement • Customers will have a better experience overall • Staff will have a better experience – will have cup filled up by being able to meet the needs of customers • More responsive functionality as we adopt new grants & programs • Save money by stopping paying for services we won’t need any longer • More time to create innovative service delivery models • Compliance – less time and easier to meet • Intuitive to use and checks and balances are built in | • Happy employees • Happy customers • Less duplication and wait times • More important and timely reports • Shorter appointments due to a more streamlined process • Great productivity • More time to spend with customer with value adds vs. data entry • Reduce errors due to time outs • We will meet all federal guidelines and be compliant in all our programs | • Happy customers; improved relationship between IT/EC/LWDB WorkSource partnership • Reduction in tickets which is a byproduct of success and meeting users’ needs • Data migrates successfully • Accuracy in data and reporting • Can work proactively on future opportunities and not in firefighting mode to make changes • Modernized platform aligns with agency strategy • Good vendor relationship and accountability • Solid hand-off with vendor • Proper succession planning, funding, resources, etc., for maintenance and operations • Adequate training for IT staff and users • Project is completed within scope, schedule, and budget after robust testing and buy-in from all stakeholders across the WorkSource partnership
Awareness | • 30-minute monthly meetings dedicated to WIT with all staff • 1st meeting, we will share this plan • Celebrate milestones, people, and accomplishments • Promote townhalls and encourage participation • Listening sessions or focus groups (demonstrate where we are at and allow for staff feedback) • Targeted communications around programs being worked on at that time • Promote WPC site and do demos of the site during meetings • Encourage supervisors to attend Navigating Change for Leaders | • Celebrate milestones, people and accomplishments • Promote townhalls and encourage participation • Listening sessions or focus groups (demonstrate where we are at and allow for staff feedback) • Provide opportunities to participate in hands on sprint demo’s • Promote WPC site and do demos of the site during meetings • Encourage supervisors to attend Navigating Change for Leaders Communicate – • Here were your pain points but this is how we are fixing them • Targeted communications around programs being worked on at that time • Plan a communication every other month opposite of the WIT Town Hall • Create a gov delivery distribution list for all staff to track engagement (Cam, Jaide & Emma) • Monthly agenda topic on all staff meetings | Communication • Features and benefits • Improvements • What will we be getting • Here were your painpoints but this is how we are fixing them • Partnership Management Team – include in monthly agenda topic • Promote bi-monthly townhalls and recordings • Promote WPC – WIT project page | • Every other month opposite of the WIT Town Hall – plan a communication • Quarterly Town Hall – Topic • Demo sprints – Show me • Consolidated brief – a couple bullet points (42 characters - 10 words or less) • Flag important emails and highlight what they really need to know (maybe weekly roll -up) • Gamify – to encourage them to play. Like a WIT badge of knowledge (kahoot game) "Keep your WITS" "Don't lose your WITS" Collect your WITS" "Battle of the WITS" • Navigating Change for Leaders (assessment of who has taken it) | • Access to the data, in a useable format • Create ad hoc queries from the database • Less burden in the documentation process • If there’s complaining, then successful • User-friendly platform that gets us the information we can use/we need • Will start winning people over once they get to touch and feel new product • Ability to make useful, accurate decisions on processes, on how the system operates, using the data on how we do business | • Updates at staff meetings • Leverage ‘talking points’ document • Use common language • Leverage all modalities • Ask questions to gauge • E-mail updates • Newsletter • TEAMs • 1:1’s • Town Halls • Internal SharePointe | • Celebrate milestones, people and accomplishments • Listening sessions or focus groups (demonstrate where we are at and allow for staff feedback) • Provide opportunities to participate in hands on sprint demo’s • Encourage supervisors to attend Navigating Change for Leaders Communicate – • Here were your pain points but this is how we are fixing them • Promote townhalls and encourage participation • Targeted communications around programs being worked on at that time • Plan a communication every other month opposite of the WIT Town Hall • Create a gov delivery distribution list for all staff to track engagement (Cam, Jessica & Carson) • Monthly agenda topic on all staff meetings • Promote WPC site and do demos of the site during meetings | • Multiple orientations and trainings • Pulse checks to gauge staff understanding • Strategic communications, avoiding overload or over communicating • At administrator and supervisor level, huddles, staff meetings, all staffs, 1:1’s • TEAMS channel strategic updates and interaction opportunities • Use a common language when discussing this project; need consistency • Newsletter updates • E-mail updates (keeping them to a minimum) | • Multiple orientations and trainings • Guinea pigs, “work groups” or breakout groups. • Pulse checks to gauge staff understanding • Strategic communications, avoiding overload or over communicating • Posters that ETO is being replaced • At administrator and supervisor level, huddles, staff meetings, all staffs, 1:1’s • Heads-up during ETO trainings • TEAMS channel strategic updates and interaction opportunities • Use a common language when discussing this project; need consistency • Newsletter updates • E-mail updates (last resort) | • Regular emails with updates --- hints, tidbits • Quarterly WIT meetings with all partner and internal – increase as needed or get closer to launch • Create a timeline of what we are working on it so easy to share – visual • Trainings | • Identify who needs to be aware – • TC Futures, WDC, ESD, & Career Path Services • Leadership at partnerships L&I, OIC, CBC • Inform partners who have historically not used ETO • Standing agenda item at least monthly • WCB all staff, TC Futures all-staff, ESD staff meeting, WDC all staff, Career Path all staff • BFWDC Board meeting • Promote Bi-monthly town halls & recordings • Targeted communications around programs being worked on at that time • Promote the WPC WIT Update page • Survey – asking how to increase awareness • Shout out on the BFWDC website Bi-monthly sending them to the WPC WIT page • POC – Who can people reach out to if they have questions | • Constant communication – Keep in loop. • Town halls • Email – big wins, most exciting add visuals, screenshots • Sneak peaks • Talking points – for leaders that they could use in huddles, meetings • Promote WPC WIT page – do walk thru’s • All-Staff meetings (WorkSource centers) – monthly topic • Create opportunities for feedback thru focus groups • Opportunities for hands on / testing • Sandbox | • Division town halls • Leverage ‘talking points’ document packet • IT division Pulse emails • 1:1s • Team huddles • Trivia
Desire | Today the desire is strong staff is looking forward to the change. We will continue to drive desire by: • Explaining the benefits – speed, time outs, less re-work, more automation, less workarounds, less duplicity • Show - Contrast and compare – new vs current • Ask - What would a good version of ETO look like to you in meetings and 1 on 1’s • Ask - If you had unlimited budget what would be the top 3 things you would fix in ETO in meetings and 1 on 1’s | We will continue to drive desire by: • Explaining the benefits – speed, time outs, less re-work, more automation, less workarounds, less duplicity • Show - Contrast and compare – new vs current • This is what it looks like now – this is how we are changing it? • Awards (trinkets, swag) for attending orientations/ trainings • Ask – What would be the top 3 things you would fix in ETO in meetings and 1 on 1’s | Today the desire is strong staff is looking forward to the change. We will continue to drive desire by: • Continue to talk about the benefits | Today the desire is strong staff is looking forward to the change. We will continue to drive desire by: • Share the wins as they come • WIIFM – be ready to answer this when we can, as soon as we can • Strategic on how we talk about the benefits --- when talking with frontline share frontline benefits, leaders share what matter to them (data) • Incentives | • ‘ETO is going away’ is motivation enough • Focus on the positives, more in intuitive system • Awards (trinkets, swag) for attending orientations/ trainings • Take user input and utilizes it (and people see that), there’s buy-in, folks feel apart of the change | • SMEs participate in development • Change Champions • Staff voice sharing with peers • Use video snippets to markets (trailers) • Ensure folks feel heard, are part of the process, suggestions are considered | We will continue to drive desire by: • Explaining the benefits – speed, time outs, less re-work, more automation, less workarounds, less duplicity • Show - Contrast and compare – new vs current • This is what it looks like now – this is how we are changing it? • Awards (trinkets, swag) for attending orientations/ trainings • Ask – What would be the top 3 things you would fix in ETO in meetings and 1 on 1’s | • Focus on the positives and sell this to front line staff to get more buy in • Focus on WIIFM and have ready key points for consistent messaging • Engaging staff in questions like “what top 3 things would you fix in ETO?” • Releasing the fun tidbits of project, building it up along the way, show why they will love replacement. • Use visuals – compare and contrast – new vs current • Highlight the benefits and all the positive talking points, have handouts available | • Focus on the positives, a more intuitive system • Awards (trinkets, swag) for attending orientations/trainings and being engaged • Focus on WIIFM • Engaging staff in questions like “what top 3 things would you fix in ETO?” • Take user input and utilize it (when people see that, there’s more buy-in, folks feel apart of the change • Releasing the fun tidbits of project, building it up along the way, show why they will love replacement. • Use visuals – compare and contrast – new vs current • Highlight the benefits and all the positive talking points, have handouts available | Today the desire is strong staff is looking forward to the change. We will continue to drive desire by: • Open floor about what have you been struggling with ETO this week/month? • Examples of what you don’t like – redundancies • This is what it looks like now – this is how we are changing it? Contrast – Compare • Demo’s • History – why this time it is going to be different? What are we doing to make this experience better • Understanding the goal – what is it? | Today the desire is strong staff is looking forward to the change. We will continue to drive desire by: • Promote benefits • What can we reasonably expect • Demo’s when we have a product to show • Video’s of demo or protow types • Continue to articulate how this time it is different then Skyes to ETO. Engaged, teams involved to select a bidder. We heard you… articulate all the challenges and highlight how we are going to fix them. • Look for ways we can get more frontline staff involved? • Funding / incentive / make it fun (pizza parties) | Today the desire is strong staff is looking forward to the change. We will continue to drive desire by: • Highlight contrast between new systems – Contrast & Compare • Big wins • Incentive – Fun – put some splash behind (maybe a coffee cart) • Flyer – one pager fun document | • SMEs participate in development • Change Champions • Staff voice sharing with peers • Videos • Ensure folks feel heard, are part of the process, suggestions are considered
Knowledge | We are using an agile approach, which means we'll change and adjust as we go. • Advertise training schedule - Communicate schedule early and often • Encourage participation – if you want to have access you need to attend training. (MIS) • Make time and space for employees attend the training (try and take stuff off plate so can focus) • Feedback sessions after training – share with each other what we learned • Encourage people to become early adopters • Have Techy SME’s – Change champions – Bring in dissenters early on. • Train supervisors early in the process so they can support/coach their teams • Promote – support teams’ channel (what options would work for partners?) • Tips of the week - Did you know? Try this? • Use desk-aids – promote them • Recorded training sessions --- mini video’s – snippets on how to… • Differences training by program • Different training options – some all don’t learn well online, maybe some in person trainings | We are using an agile approach, which means we'll change and adjust as we go. • Advertise training schedule - Communicate schedule early and often • Encourage participation – if you want to have access you need to attend training. (MIS) • Make time and space for employees attend the training (try and take stuff off plate so can focus) • Feedback sessions after training – share with each other what we learned • Encourage people to become early adopters • Have Techy SME’s – Change champions – Bring in dissenters early on. • Train supervisors early in the process so they can support/coach their teams • Promote – support teams’ channel (what options would work for partners?) • Tips of the week - Did you know? Try this? • Use desk-aids – promote them • Recorded training sessions --- mini video’s – snippets on how to… • Differences training by program • Different training options – some all don’t learn well online, maybe some in person trainings • Share what to expect as we learn more about versions | We are using an agile approach, which means we'll change and adjust as we go. • Proactively prioritize as things come out – clear the day so staff can participate • Communicate schedule early and often • Ensure staff has time to dedicate to training • Message needs to be that training is what you are scheduled for today. (required/ priority ) • Training is critical to become experts /supervisors to drive message since they have largest impact to teams • Communicate the big why – This is why – this is how it connects to your work – direct leader positive messaging. • Train supervisors early in the process so they can support /coach their teams • Ensure we have people in for user testing so they can become SME’s | We are using an agile approach, which means we'll change and adjust as we go. • Proactively prioritize as things come out – clear the day so staff can participate • Communicate schedule early and often • Ensure staff has time to dedicate to training • Message needs to be that training is what you are scheduled for today. (required) • Make training a priority • Training is critical to become experts /Message from supervisors to drive message – so impactful to teams • Communicate the big why – This is why – this is how it connects to your work – direct leader positive messaging. • Train supervisors early in the process so they can support /coach their teams • Ensure we have people in for user testing so they can become SME’s • Dedicate time to practice and train | • One page of general information (desk aids) • Scheduled trainings • Centralized resource hub (videos, one easy-to-find) (TEAMS, Learning Exchange) • Ensuring partner meetings across the system; speaking common language • Connections site meeting where we are hitting as many players/partners as possible • Make it easy-to-use | • Short training videos • Each partner have a SME or champion available • Layered approach; multiple places to learn new system • Central repository with desk aids • TEAMs channel to ask questions | We are using an agile approach, which means we'll change and adjust as we go. • Advertise training schedule - Communicate schedule early and often • Encourage participation – if you want to have access you need to attend training. (MIS) • Make time and space for employees attend the training (try and take stuff off plate so can focus) • Feedback sessions after training – share with each other what we learned • Encourage people to become early adopters • Have Techy SME’s – Change champions – Bring in dissenters early on. • Train supervisors early in the process so they can support/coach their teams • Promote – support teams’ channel (what options would work for partners?) • Tips of the week - Did you know? Try this? • Use desk-aids – promote them • Recorded training sessions --- mini video’s – snippets on how to… • Differences training by program • Different training options – some all don’t learn well online, maybe some in person trainings | • One page of general information, make it easily consumable and easy-to-use • Start with realistic number of qualified trainers and offer lots of training, training videos, short and sweet (sound bites) • Schedule trainings and get staff involved for peer-to-peer learning • Give staff time to use it and practice; leaders need to support this time for training • Centralized resource hub with videos, helpful tips, and desk aids (one easy-to-find) • Need support from performance leaders and Senior leadership • Town Halls, perhaps play Jeopardy and other games to promote learning in fun way • Ensuring partner meetings across the system; speaking common language • Layered approach; multiple places to learn the new system; varied methodologies, local offices flush out ideas based on need | • One page of general information • Training videos, short and sweet (sound bites) • Scheduled trainings and get staff involved for peer-to-peer learning • Centralized resource hub with videos, helpful tips, and desk aids (one easy-to-find) • TEAMs channel to ask questions • Town Halls, perhaps play Jeopardy and other games to promote learning in fun way • Ensuring partner meetings across the system; speaking common language • Make it easy-to-use • Layered approach; multiple places to learn the new system; varied methodologies • Encourage people to become early adopters | We are using an agile approach, which means we'll change and adjust as we go. • Encourage leaders to participate in demo’s, workshops, early trainings & testing • Train supervisors early in the process so they can support / coach their teams • Have a SME in every office • Did you know you can do **** “weekly email” • Monthly focus trainings on variety of topics • Communicate the training schedule early and often | We are using an agile approach, which means we'll change and adjust as we go. • Disseminate information as it comes, chunk it out. Lead into a primary release and revisit the topics • Check for understanding as we go • Communicate training schedule early and often • Dedicated time for training • Supervisors and influencers (at all levels) trained first • Dedicated SME’s to create FAQ’s – tips and tricks, Did you know articles and help others | We are using an agile approach, which means we'll change and adjust as we go. • Communicate schedule early and often • Leadership communicate training is a priority and 100% behind this. (do we need to bump up staffing at this time) • Making sure enough time dedicated to training for classroom training and for practice (Maybe closing down a day if needed) • Create SME’s so staff have a resource to go to • Open access to trainers after training to get questions answered • Clear time / schedule for staff to dedicate to training and practice • FAQ’s • Recorded training so people can go back and watch – snippets (how to videos) Touchpoints • Train supervisors early in the process so they can support/coach their teams | • Short training videos • FAQs • Layered approach; multiple places to learn new system • Central repository with desk aids
Ability | We are using an agile approach, which means we'll change and adjust as we go. • Dedicated time to practice • Group sharing – shadowing understanding how it is done. • Best practices / Tips and tricks newsletters / desk drops • Positive reinforcement • Identify super users who can be the SME’s • Roving SME – walking around looking for ways to help | We are using an agile approach, which means we'll change and adjust as we go. • Dedicated time to practice • Group sharing – shadowing understanding how it is done. • Best practices / Tips and tricks newsletters / desk drops • Positive reinforcement • Identify super users who can be the SME’s • Roving SME – walking around looking for ways to help • Desk aids, YouTube videos, show different aspects of WIT • Use real life scenarios in huddles/team meetings to practice • Use games to test knowledge and understanding | We are using an agile approach, which means we'll change and adjust as we go. • Dedicate time to practice – with scenarios, list of what to do a task list • Maybe even a check list / challenge (gamify it) • Scavenger hunt with prizes • Dedicate time to practice and train --- Early in learning then again right before launch • Account for different learning styles – hands on, 1 on 1, in person, virtual • What barriers did you have with learning ETO? Learn that ahead of time so we can plan for it • Continuous learning --- SME’s host best practices sessions • Team Channel for support with SME’s • Make sure SME’s have a POC to get answers/support from | We are using an agile approach, which means we'll change and adjust as we go. • Dedicate time to practice – with scenarios, list of what to do a task list • Maybe even a check list / challenge (gamify it) • Scavenger hunt with prizes • Close to public to dedicate time to practice and train --- Early in learning then again right before launch • Account for different learning styles – hands on, 1 on 1, in person, virtual • What barriers did you have with learning ETO? Learn that a head of time so we can plan for it • Continuous learning --- SME’s host best practices sessions • Team Channel for support with SME’s | • Desk aids • Short training videos (beginner, intermediate, advanced) library • Recording of training sessions available • Knowledge-based test/real case scenario/training environment/muscle-memory exercises • Practice with above bullet, determine where more training is required • Identify best users (SME’s, change champions) | • Test model for people to practice; non-live environment • Removal of other options, workarounds • Create ‘admin’ days for learning, practice of new system | We are using an agile approach, which means we'll change and adjust as we go. • Dedicated time to practice • Group sharing – shadowing understanding how it is done. • Best practices / Tips and tricks newsletters / desk drops • Positive reinforcement • Identify super users who can be the SME’s • Roving SME – walking around looking for ways to help • Desk aids, YouTube videos, show different aspects of WIT | • Desk aids, YouTube videos, show different aspects of WIT • Short training videos (beginner, intermediate, advanced) library • Recording of training sessions and make them available • Knowledge-based test/real case scenario/training environment/muscle memory exercises • Practice with above bullet, determine where more training is required • SME’s being actively used in the development of training goals • Test model for people to practice; non-live environment | • Desk aids • Short training videos (beginner, intermediate, advanced) library • Recording of training sessions and make them available • Knowledge-based test/real case scenario/training environment/muscle memory exercises • Practice with above bullet, determine where more training is required • Identify best users (SME’s, change champions, etc.) • Test model for people to practice; non-live environment • Create ‘admin’ days for learning and practice | We are using an agile approach, which means we'll change and adjust as we go. • Did you know you can do **** “weekly email” • Monthly focus trainings on variety of topics • Allow time to play in sandbox – dedicated time to practice • Allow time to spend with SME • Ensure employees have access to knowledge and support when needed • Roving (walking) SME – walking around looking for ways to help • Allow time to provide feedback • Chat bot, virtual assistants, help desk, phone lines | We are using an agile approach, which means we'll change and adjust as we go. • Dedicated time to practice (sandbox) • Create workload capacity to ensure they have time to practice • Take stuff off the plate so they have time to practice – What can we take a break from this quarter (cancel some meetings) (allow time and alleviate stress) • Repurpose scheduled meetings to training/practice time with scenarios • Small group sessions – structured around adult learning styles • Tools that support different learning styles – videos, FAQ’s, tips and tricks, best practices | We are using an agile approach, which means we'll change and adjust as we go. • Allow time for practice • Hands on training • SME’s • Sandbox • Support team channel • Supervisors supporting or arranging support with trainer or SME for those who need extra help. • Did you know … Tips and tricks | • Test model for people to practice; non-live environment • Create ‘admin’ days for learning, practice of new system • TEAMs channel/group email inbox to ask questions
Reinforcement | We are using an agile approach, which means we'll change and adjust as we go. • Celebrate milestones • Recognize and create champions • Continue to check in for technical guidance and ask questions • Share success stories • Celebrate benefits, metrics and easy attainable data (we have come this far) • More time with customers vs data entry | We are using an agile approach, which means we'll change and adjust as we go. • Define milestones and celebrate them • Recognize and create champions • Continue to check in for technical guidance and ask questions • Share success stories and lessons learned • Celebrate benefits, metrics and easy attainable data (we have come this far) • More time with customers vs data entry • Formalized quality team that goes out and reviews data entry and gives awards • Sponsor messages celebrating successes | We are using an agile approach, which means we'll change and adjust as we go. • Celebrate by using dashboard data (strong users) • Success stories – market and promote • Lessons Learned • Standard agenda topic to discuss successes, concerns and best practices at team and system level • Kudos | We are using an agile approach, which means we'll change and adjust as we go. • Celebrate by using dashboard data (strong users) • Success stories – market and promote • Lessons Learned • Standard agenda topic to discuss successes, concerns and best practices at team and system level • Kudos | • Accountability • Sample auditing, sharing data and what it shows us/tells us • Celebrating the wins, accentuate the positive • Identifying gaps • Be positive with messages • Transparency (that we’re all looking at it) • Solicit ideas for further improvements (will the new product be nimble enough?) • Refresher/recurrent training or a continuum of learning | • Helpful if staff can see ‘dashboard’ in real-time • Ability to see the wins (qualitative) • Rewards • Celebrations of milestones • Reinforce the quality of input, using outputs for coaching • Recognize behaviors we want repeated | We are using an agile approach, which means we'll change and adjust as we go. • Celebrate milestones • Recognize and create champions • Continue to check in for technical guidance and ask questions • Share success stories and lessons learned • Celebrate benefits, metrics and easy attainable data (we have come this far) • More time with customers vs data entry • Formalized quality team that goes out and reviews data entry and gives awards | • Communication and huddles, keep them going, pulse checks • How is it going? What are the challenges? What needs to be addressed? • Sample auditing, sharing data and what it shows us/tells us, • This will acknowledge performance measures and why they matter • Celebrate milestones and wins, accentuate the positive, give kudos • Identifying gaps • Be positive with messages • Transparency (that we’re all looking at it) • Solicit ideas for further improvements (will the new product be nimble enough?) • Refresher/recurrent training or a continuum of learning • Helpful if staff can see ‘dashboard’ in real-time • Ability to see the wins (qualitative) • Reinforce the quality of what is input; using outputs for coaching purposes, not punitive • Recognize / acknowledge behaviors we want repeated • Share experiences, best practices, lessons learned, “quick tips” | • Communication and huddles, keep them going, pulse checks • How is it going? What are the challenges? What needs to be addressed? • Sample auditing, sharing data and what it shows us/tells us, • This will acknowledge performance measures and why they matter • Celebrate milestones and wins, accentuate the positive, give kudos • Identifying gaps • Be positive with messages • Transparency (that we’re all looking at it) • Solicit ideas for further improvements (will the new product be nimble enough?) • Refresher/recurrent training or a continuum of learning • Helpful if staff can see ‘dashboard’ in real-time • Ability to see the wins (qualitative) • Reinforce the quality of what is input; using outputs for coaching purposes, not punitive • Recognize / acknowledge behaviors we want repeated • Share experiences and lessons learned/feedback | We are using an agile approach, which means we'll change and adjust as we go. • As it is built – highlight successes. Take the pain points and start talking about differences or how much it will be better in WIT • Before & After – show illustrations on how it will work • Desk aids – ask me about our new an improved website • Success stories / testimonials • Pulse Checks | We are using an agile approach, which means we'll change and adjust as we go. • Collect feedback from employees thru focus groups & surveys • Celebrations at milestones / successes • Lessons Learned • Lunch and learns (snack & study) • Success stories – market & promote • A day in the life --- ETO VS New tool • Practicing gratitude and how the system is better. | We are using an agile approach, which means we'll change and adjust as we go. • Share lesson learned • Share best practices • Celebrate successes • Promote time differences / how much faster it is to do things • Pulse checks - in team meetings • Focus groups • What did we learn, what did we like • Share reports / dashboards • Reinforcing where you can get help or POC • FAQ’s – Make sure know who creates and how it gets maintained | • Helpful if staff can see ‘dashboard’ in real-time • Share the wins • Celebration of milestones • Recognize behaviors we want repeated • Use feedback loops

## Approach & Strategies
Counties
LWDB
Region
Director / CEO
Regional Director
OCM Team
Sponsor(s)
Change Manager
Subject Matter Experts
The plan details
Who will approve this plan?
Who will be the approved sender of messages?
How often will team meet in 2023
How will the team share information
How will this team seek out feedback? Feedback loops
Why are we replacing ETO?
Strengths
Opportunites
What will success look like?
ADKAR Methodology and Planned Steps to Support Change
Awareness
Desire
Knowledge
Ability
Reinforcement